## Tasks
Date | Activity | Status | Responsibility
2026-07-25 | Hotbox - all 4 walls erection completion |  | ME
2026-07-28 | Meeting with BHEL Dir Power | Completed | P&S
2026-08-03 | UNIT#3 hot box Side plate erection by 03.08.26 | Completed | ME
2026-08-10 | ISH Foundation handover | Completed | CCD
2026-08-14 | Boiler DHT - Target completion | Delayed R0- 25-07-26 | ME
2026-08-14 | 1st HT Switchgear charging | Delayed R0 - 25-07-26 | EED
2026-08-14 | Bottom ash Hopper foundation handover | Delayed R0- 05-08-26 | CCD
2026-08-17 | 2nd TDBP Deck Casting |  | CCD
2026-08-17 | MPH Columns casting completion and scaffolding removal |  | CCD
2026-08-20 | Transfer Tower Foundation handover |  | CCD
2026-08-25 | Tripper floor structure works completion |  | ME
2026-08-25 | ESP-CR 8.5m structure works completion |  | ME
2026-08-30 | Cable rack - Foundation LHS/RHS Completion | Delayed R0- 14-08-26 | CCD
2026-08-30 | BAIS Silo foundation handover |  | CCD
2026-08-30 | AHP Stg-1 and Stg-2 Foundation handover |  | CCD
2026-08-31 | TG Box up - Target completion |  | ME
2026-09-05 | ESP-CR 8.5Mm slab casting |  | CCD
2026-09-15 | Start of LP Turbine erection after hotbox completion |  | ME
2026-10-31 | TG Oil Flushing completion |  | C&T
2026-11-15 | Boiler Light up |  | C&T
2026-12-25 | Steam Blowing Completion |  | C&T
2027-02-07 | Sync |  | C&T
2027-02-25 | Full Load |  | C&T
2027-03-15 | Trial Operation |  | C&T