## Updates
Date | Category | Update
46237 | ACC | Tonnage - Daily - 10, Week - 100; Month - 1000; Aug month target
46238 | Boiler | NDHT Balance joints - 12950. Aug - 0; DHT Balance joints - 238
46239 | PCP Joint | MS Joints - 26/146; MS to PRDS - 4/26; HRH - 6/95; CRH - 6/87; LPBP - 4/33; HPBP - 4/49; BFD- 120/661
2026-08-11 | ACC | 10.08.26 - Manpower - 270nos; Tonnage erected - Saturday - 12.85; Aug 1st week - 68.83; Aug - 81.7; Total - 2770 (submitted by Test User, test.user@ntpc.co.in)

## Critical areas
Date | ACC | Boiler - NDHT Joints | PCP - P91/92
Target | 30 | 200 | 2
2026-08-10 | 19.3 | 10 | 0
2026-08-09 | 12.8 | 0 | 0
2026-08-08 | 0 | 0 | 0
2026-08-07 | 32 | 0 | 0
2026-08-06 | 15.7 | 0 | 0
2026-08-05 | 0 | 0 | 1
2026-08-04 | 0 | 0 | 1

## Chimney
Segment | Date
Segment-1 | Erected
Segment-2 | 2026-08-14
Segment-3 | 2026-09-20
Segment-4 | 2026-10-26
Segment-5 | 2026-11-30